## Sheet1
Project Forecast Plan of SPPL Project
Project Owner: Md. Ahamudul Hoque
# | Task Title | Responsible | Dateline | Status
1 | Provide Complete Feature List to SPPL. | Genweb2 | 08-12-2021
2 | SPPL will provide a feedback to Genweb2 based on the Feature list. | SPPL | 14-12-2021
3 | Genweb2 and SPPL both confirm & finalize their feature list with agreement. | SPPL & Genweb2 | 15-12-2021
4 | Genweb2 will Provide a Master Data template to SPPL for master data capturing. a) Product Category b) Unit Of Measure c) Product d) Location | Genweb2 | 28-11-2021
5 | According to the template, SPPL sends back the template to Genweb2 with associate master data. | SPPL | 31-12-2021
6 | Genweb2 will prepare UAT Server | Genweb2 | 20-01-2022
7 | Genweb2 will upload all master data into the system. Including Employee Info & Vendor Details. | Genweb2 | 31-01-2022
8 | Genweb2 will provide Training & UAT sessions within the mentioned date. | SPPL & Genweb2 | 7-02-2022 to 15-02-2022
9 | Genweb2 will Prepare Live Server | Genweb2 | 20-02-2022
10 | Genweb2 will Incorporate the minor feedback (Which was occurring through UAT Session). | Genweb2 | 26-02-2022
11 | SPPL Provide Cut Of Balance through predefined template. | SPPL | 26-02-2022
12 | Upload Cut Of Balance into Live Server. | Genweb2 | 27-02-2022
13 | Go to the Live. | Genweb2 | 28-02-2022
14 | Support (3 Month Free Support) | Genweb2 | 01-03-2022 to 30-05-2022