## SRS component Deadline
| Module | Task | Activity | Require day | Date | Week
| Merchandising | review | meeting with client |  |  | 43
| Procurement |  | internal meeting
| Inventory |  | srs modification
| Commercial | SRS | Process Flow Diagram | 0.5 | 2015-10-25 | 44-45
Merchandising |  |  | Process Description | 0.5 | 2015-10-25
Procurement |  |  | Usecase | 0.5 | 2015-10-26
Inv |  |  | Usecase Diagram | 0.5 | 2015-10-26
Com |  |  | Usecase Table | 3 | 2015-10-29
Planning |  |  | Mocup | 1 | 2015-11-01
T&A |  |  | srs compilation & Review | 0
Production |  | review | meeting with client | 1 | 2015-11-02
Acc |  |  | internal meeting | 0
Delivery |  |  | srs modification | 1 | 2015-11-03
| Production Planning | SRS | Process Flow Diagram | 0.5 | 2015-11-04 | 45-46-47
|  |  | Process Description | 1 | 2015-11-05
|  |  | Usecase | 1 | 2015-11-08
|  |  | Usecase Diagram | 0.5 | 2015-11-09
|  |  | Usecase Table | 2 | 2015-11-11
|  |  | Mocup | 2 | 2015-11-15
|  |  | srs compilation & Review | 1 | 2015-11-16
|  | review | meeting with client | 1 | 2015-11-17
|  |  | internal meeting | 0 | 2015-11-22
|  |  | srs modification | 2 | 2015-11-18
| Time & Action | SRS | Process Flow Diagram | 0.5 | 2015-11-19 | 47-48-49
|  |  | Process Description | 0.5 | 2015-11-19
|  |  | Usecase | 0.5 | 2015-11-22
|  |  | Usecase Diagram | 0.5 | 2015-11-22
|  |  | Usecase Table | 2 | 2015-11-24
|  |  | Mocup | 1 | 2015-11-25
|  |  | srs compilation & Review | 0 | 0
|  | review | meeting with client | 1 | 2015-11-26
|  |  | internal meeting | 0
|  |  | srs modification | 1 | 2015-11-29
| Production Management | SRS | Process Flow Diagram | 0.5 | 2015-11-30 | 49-50-51
|  |  | Process Description | 0.5 | 2015-11-30
|  |  | Usecase | 0.5 | 2015-12-01
|  |  | Usecase Diagram | 0.5 | 2015-12-01
|  |  | Usecase Table | 3 | 2015-12-06
|  |  | Mocup | 2 | 2015-12-08
|  |  | srs compilation & Review | 1 | 2015-12-09
|  | review | meeting with client | 1 | 2015-12-10
|  |  | internal meeting | 0
|  |  | srs modification | 1 | 2015-12-13
| Accounting | SRS | Process Flow Diagram | 0.5 | 2015-11-08 | 46-47-48-49
|  |  | Process Description | 0.5 | 2015-11-09
|  |  | Usecase | 0.5 | 2015-11-15
|  |  | Usecase Diagram | 0.5 | 2015-11-16
|  |  | Usecase Table | 3 | 2015-11-22
|  |  | Mocup | 1 | 2015-11-29
|  |  | srs compilation & Review | 1 | 2015-11-30
|  | review | meeting with client | 1 | 2015-12-01
|  |  | internal meeting | 0
|  |  | srs modification | 1 | 2015-12-03
| Shipment Management | SRS | Process Flow Diagram | 0.5 | 2015-12-06 | 50-51 | 2015-11-16
|  |  | Process Description | 0.5 | 2015-12-07 |  | 2015-11-17
|  |  | Usecase | 0.5 | 2015-12-08 |  | 2015-11-18
|  |  | Usecase Diagram | 0.5 | 2015-12-09 |  | 2015-11-19
|  |  | Usecase Table | 1 | 2015-12-10 |  | 2015-11-22
|  |  | Mocup | 1 | 2015-12-13 |  | 2015-11-23
|  |  | srs compilation & Review | 1
|  | review | meeting with client | 1 | 2015-12-14
|  |  | internal meeting | 0
|  |  | srs modification | 1 | 2015-12-15