## Sheet1
Module | Process | Interface | Change Request | Comments
Inventory | Gate Pass | Gate Pass In | Need to incorporate | Incorporated
|  | Gate Pass Out | Need to incorporate | Incorporated
| Excess item Receive Process | Inventory Receive | Access item qty receive option will be incorporated in system | Incorporated
| QC Process | Inventory QC | Item wise QC required and not required configuration needs to be incorporated in system. | Will be added in Item Master Level
| Allocation/De-allocation/Re-allocation Process | Allocation/De-allocation/Re-allocation | Available quantity need to be added in grid as a user information | Incorporated
| Inventory Issue Process | Inventory Issue | Indent number will be incorporated in grid level to allow inventory issue against multiple Indent | Incorporated
| Store Item Transfer Process | Inventory Transfer | There will be only one transfer interface | Incorporated
|  |  | Transfer will affect the stock at the same time while transiction take place whether physical inventory will be transferred later. Lakhsma will crosscheck the stock report at the day end so it will be managed. | Incorporated
|  |  | No intransit item/quantity will be allowed to loss/mismatch/damage. | Incorporated
Procurement | PO Tolerance Process | Purchase Order | Tolerance option need in PO and Inventory can't receive more than PO+tolerance qty. | Incorporated
| PO Amendment Process |  | SPO can be amended if PO/Item is yet to receive | Incorporated
|  |  | If PO/Items has received then SPO can't be amended, New PO have to be created | Incorporated
|  |  | Amendment will be in a popup, PO can't be edited. | Incorporated
|  |  | Amendment button will not appear if PO is not approved, After approval if admin allow the amendment then the amendment button will appear to user and after amendment approval will require, only approved amendment will be effective | Incorporated
| Item row by PO allocation Process |  | EPO field will be added in grid level to to add PO for multiple EPO | Incorporated